## Sheet1
Category | Work Item | Status | Cost | Deadline | Owner
Git | Research how to use Github | Done | 1 hour | 2019-06-03 | Jackson
Documentation | Create and fill out the Project Charter | Done | 30 minutes | 2019-06-10 | Kyle
Documentation | Create and fill out the Work Breakdown | Done | 30 minutes | 2019-06-10 | Kyle
Logic | Research other text-based adventure games | Done | 30 minutes | 2019-06-03 | Nick
Logic | Create flowchart of story | Done | 4 hours | 2019-06-05 | Kyle & Nick
Git | Create and test Git repository | Done | 2 hours | 2019-06-06 | Jackson
Alexa | Research creating Alexa skills | Done | 4 hours | 2019-06-06 | Jackson
Logic | Develop the logic structure of the game | Done | 30 minutes | 2019-06-06 | Kyle
Alexa | Create Alexa skill | Done | 5 hours | 2019-06-10 | Jackson & Siddhu
Alexa/Logic | Integrate logic and Alexa skill | Done | 8 hours | 2019-06-10 | Jackson & Siddhu
Documentation | Maintain work log and other documentation | Done | 1 hour | 2019-06-10 | Kyle