## Sheet1
Date | Task | Time Spent | Task Completed? | Who Completed? | This spreadsheet is not the work breakdown; will be used later to form it
2019-05-28 | Research how to use Github | 20 minutes | No | Jackson
2019-05-28 | Create and format the Project Charter | 10 minutes | Yes | Kyle
2019-05-28 | Create and format the Work Breakdown | 10 minutes | Yes | Kyle
2019-05-30 | Research how to use Github | 20 minutes | No | Jackson
2019-05-30 | Fill out the Project Charter | 20 minutes | No | Kyle
2019-06-03 | Research how other text based games work | 30 minutes | Yes | Nick
2019-06-04 | Research how to use Github | 30 minutes | Yes | Jackson
2019-06-04 | Create flowchart of game story | 30 minutes | No | Nick
2019-06-05 | Create Git Repository | 45 minutes | No | Jackson
2019-06-05 | Fill out the Project Charter | 45 minutes | Yes | Kyle
2019-06-05 | Create flowchart of game story | 45 minutes | No | Nick
2019-06-05 | Test Git Repository | 45 minutes | Yes | Jackson & Kyle
2019-06-05 | Research creating basic Alexa skills | 2 hours | No | Jackson
2019-06-05 | Develop the logic structure | 30 minutes | No | Siddhu
2019-06-05 | Create flowchart of game story | 3 hours | Yes | Kyle
2019-06-05 | Connecting utterances to intents | 30 minutes | No | Siddhu
2019-06-05 | Develop the logic structure | 30 minutes | Yes | Kyle
2019-06-06 | Format story into text document | 30 minutes | Yes | Kyle
2019-06-07 | Research creating basic Alexa skills | 1 hour | Yes | Jackson
2019-06-08 | Create a basic Alexa skill | 3 hours | No | Jackson
2019-06-09 | Continued work on basic Alexa skill | 3 hours | No | Jackson
2019-06-10 | Finished basic Alexa skill in AWS + Dev Console | 2 hours | Yes | Jackson & Siddhu
2019-06-10 | Integrating game logic into Alexa skill | 8 hours | No | Jackson & Siddhu